# Meeting Minutes — Novo Nordisk Discovery Call

Date: 2026-05-06
Time: 14:00–14:45 CEST
Location: Beroe Zoom
Beroe team: Anand Kaliappan, Harish Kumar (CSM), Purnima Iyer (Solutioning)
Novo Nordisk: Lars Andersen (Global Category Director), Mette Hansen (CPO)

## 1. Context

Novo Nordisk is consolidating MRO and indirect-spend procurement across EMEA following the 2025 acquisition of three regional manufacturing sites. Annual addressable spend is approximately $480M with current category fragmentation across 12 country buying centres. Lars confirmed the executive sponsor is Mette Hansen and that the program has board-level visibility for Q3 2026.

## 2. Engagement objective

Reduce MRO procurement cost by 14% within 18 months while maintaining supplier OTIF above 96%. Build a single source of category intelligence covering laboratory consumables, packaging, and contract manufacturing. Success metric: $67M run-rate savings and a single benchmark dashboard by Q2 2027.

## 3. Categories in scope

Laboratory consumables (highest priority — 32% of addressable)

Sterile packaging (mid-priority, dual-source mandate from compliance)

Contract manufacturing organisations (long lead times, requires deep market intel)

MRO indirect (lower priority, parked for Phase 2)

## 4. Decisions taken

Beroe will deliver a baseline category benchmark for laboratory consumables by 2026-06-15.

Mette approved a paid pilot at $85K covering EMEA scope, contract starting 2026-05-20.

Single point of contact for the engagement: Lars Andersen.

Quarterly executive readouts; first one scheduled for 2026-08-30.

## 5. Action items

Action: Anand to send mutual NDA + pilot SOW by 2026-05-09.

Action: Harish to set up weekly 30-min cadence with Lars starting 2026-05-13.

Action: Purnima to share the laboratory-consumables supplier benchmark template by 2026-05-16.

Action: Lars to share current spend cube and supplier list under NDA by 2026-05-12.

Action: Mette to confirm budget owner sign-off for Phase 2 (MRO indirect) by 2026-07-01.

## 6. Risks & open questions

Compliance has flagged a dual-source mandate for sterile packaging — may constrain savings ceiling.

Contract manufacturing market intel is sparse below the top 5 CMOs; may require custom primary research.

Open: does Novo's existing Coupa instance support the proposed dashboard, or is a separate workspace needed?

## 7. Next meeting

2026-05-13, 14:00 CEST — Beroe Zoom. Topic: NDA + SOW review with Lars and Mette.