# Value Proposition Deck — Novo Nordisk

EMEA Procurement Intelligence Engagement
Prepared by Beroe · 2026-05-15 · Lead: Purnima Iyer (Solutioning Manager)

## 1. Customer context

Novo Nordisk's EMEA procurement organisation is consolidating $480M of indirect and MRO spend after the 2025 Sanofi-API and Catalent acquisitions. Twelve country buying centres operate independently today. The CPO (Mette Hansen) and Global Category Director (Lars Andersen) sponsor a board-level transformation with quarterly readouts.

## 2. Proposed solution

Beroe will deliver a managed Procurement Intelligence engagement covering laboratory consumables, sterile packaging, and contract manufacturing organisations (CMOs). The scope includes:

Quarterly category benchmarks (price, supply concentration, OTIF) for the three priority categories.

A custom EMEA-focused supplier dashboard integrated with Novo's Coupa instance.

Dedicated analyst pair for fast-turnaround should-cost models and supplier benchmarks.

Monthly executive briefings to Mette Hansen and Lars Andersen, with ad-hoc deep dives on demand.

Risk-monitoring service with weekly alerts on the top 25 critical suppliers.

## 3. Engagement shape

Engagement type: Subscription (managed service)
Duration: 18 months, with a 90-day pilot phase
Pilot start date: 2026-05-20
Full engagement start: 2026-08-20

## 4. Value themes

Cost reduction — 14% MRO procurement cost reduction within 18 months.

Risk mitigation — sub-24h response on supplier disruption events (vs current 14 days).

Category intelligence — single source of truth across 12 buying centres in EMEA.

Supplier consolidation — rationalise 220 active suppliers down to 110 strategic.

Compliance — dual-source mandate for sterile packaging fully tracked via the dashboard.

## 5. Value definition

Value is measured against three KPIs reviewed quarterly with the steering committee. (1) Realised category cost savings versus a frozen 2025 baseline, audited by Novo's internal finance team. (2) Supplier OTIF improvement, tracked weekly and rolled up monthly. (3) Reduction in time-to-decision on supplier escalations (from days to hours). Beroe commits to publishing the scorecard and a written explanation of any variance every quarter.

## 6. Estimated value

Year-1 run-rate savings: $32M
Cumulative 18-month value: $67M
Beroe engagement fee: $1.8M (subscription, 18 months)
Net value to Novo: $65.2M (≈ 36× ROI)

## 7. Commercials

Pilot fee: $85K (90 days, fixed). Convertible into the full subscription at signature. Subscription fee: $100K/month for 18 months including all deliverables in section 2. Out-of-scope work billed at a pre-agreed day rate. Termination for convenience after month 6 with 60 days' notice.

## 8. Why Beroe

Deepest category coverage in laboratory consumables and sterile packaging in EMEA.

Existing relationships with 18 of Novo's top 25 strategic suppliers.

Production-grade Procurement Intelligence platform already in use at 4 of the top 10 European pharma companies.

Senior solutioning team (avg 14 years CPG/Pharma category management experience).

## 9. Next steps

Sign mutual NDA — 2026-05-09 (already drafted).

Pilot SOW circulated for legal review — 2026-05-12.

Pilot kickoff with Lars + Purnima — 2026-05-20.

First steering committee with Mette — 2026-08-30.